SchoolOS Production Development Plan 2026 – 2028 ¦ Nepal ¦ Montessori to Class 10

Overview SchoolOS is a multi-tenant SaaS platform built for Nepal's school ecosystem — from Montessori to Class 10. It integrates admissions, attendance, fee management, academics, HR & payroll, accounting, library, transport, and communication into a single unified platform. This document outlines the phased production execution plan from foundation to AI-powered scale.

# Strategic Principles

Before phases — understand these non-negotiable architectural decisions:

| Multi-Tenant SaaS | Every record scoped to school_id. Tenant isolation at database and API layer. Not a single-tenant app. |
| --- | --- |
| Core Dependency | Module 1 (Admissions) is the root. Every other module reads student records. Build and stabilize M1 first. |
| Go Live Early | Target live school onboarding by Month 3–4. Real usage surfaces issues training data never will. |
| Early Launch + Feedback | Launch Basic Plan (M1, M2, M3, M5, M10) — enough to onboard real schools and start the feedback loop. |

# Module Overview

SchoolOS is organized into 10 core modules delivered across 4 phases:

| Module | Name | Key Focus |
| --- | --- | --- |
| M1 | Admissions & Student Profile Management | Root module — all others depend on it |
| M2 | Attendance Management | 3-tap UX — <30 seconds for teacher |
| M3 | Fee Management | VAT-compliant collection + auto journal posting |
| M4 | Academic: Exams, CAS & Grading | MoEST grading — server-locked logic |
| M5 | Activity Feed & Milestones | Primary parent retention engine |
| M6 | Homework & Timetable | Conflict detection + submission tracking |
| M7 | Staff Management, HR & Payroll | PF, TDS, leave integration |
| M8A | Library Management | Catalog, issue/return, fine integration |
| M8B | Transport Management | Routes, driver app, boarding notifications |
| M9 | Accounting & Financial Management | Double-entry GL — competitive differentiator |
| M10 | Notices, Events & Messaging | FCM push, SMS fallback, consent management |

PHASE 0 Foundation • Month 0 – 1

Goal: Set up production-grade architecture BEFORE writing any feature code. Everything built in later phases depends on this foundation being correct.

## Monorepo Setup (Turborepo)

Apps:

- api — NestJS backend

- web-admin — Next.js (React) admin dashboard

- mobile-parent — Flutter parent & teacher app

Shared packages:

- @core/auth — JWT, OTP, RBAC guards

- @core/db — Prisma schema, migrations

- @core/types — Shared TypeScript interfaces

## Backend Core

- NestJS modular architecture

- Prisma schema with multi-tenant school_id scoping

- PostgreSQL (primary datastore)

- Redis — sessions and queue management

- BullMQ — async job processing

## Authentication System (Build First)

Critical: The auth system is the platform backbone. Everything depends on this.

- JWT + refresh token rotation

- OTP system via SMS

- Role-Based Access Control (RBAC) guards

- Multi-tenant isolation — all queries scoped by school_id

## DevOps & Infrastructure

- Docker (dev + production configurations)

- CI/CD via GitHub Actions

- Environments: dev, staging, production

- Cloudflare R2 — file and image storage with signed URLs

- Firebase Cloud Messaging — push notifications

- VPS / AWS / DigitalOcean cloud hosting

PHASE 1 Core MVP • Month 1 – 4

Goal: Go live with a real school. Real usage, real feedback, real revenue.

## Modules Delivered

| Module | Name | Key Focus |
| --- | --- | --- |
| M1 | Admissions & Student Profile | Root module — stabilize before all others |
| M2 | Attendance | 3-tap UX, offline-first SQLite sync |
| M3 | Fee Management | VAT receipt, auto accounting journal posting |
| M5 | Activity Feed | Photo posts, push notifications — retention engine |
| M10 | Notices & Messaging | FCM push, SMS fallback, consent management |

## Sprint Breakdown

| Sprint | Focus | Critical Note |
| --- | --- | --- |
| Sprint 1–2 | M1 Admissions — Student CRUD, guardian linking, document upload, Student ID generation | Most important module — root of all data |
| Sprint 3 | M2 Attendance — 3-tap UI, offline-first sync, status codes (P/A/L) | UX critical: must complete in under 30 seconds |
| Sprint 4–5 | M3 Fee — Structure engine, invoice generation, VAT receipts, payment recording | Include auto journal posting stub for M9 |
| Sprint 6 | M10 Messaging — FCM push, SMS fallback, event-based triggers | Foundation for all parent communications |
| Sprint 7 | M5 Activity Feed — Photo upload, class/student tagging, push notifications | Primary retention engine — parents open daily |
| QA + Pilot | Real school testing, UX fixes, performance optimization | 2–3 weeks with live school before broad launch |

Deliverable: Basic Plan launch — Admissions, Attendance, Fees, Activity Feed, Messaging. Enough to onboard real schools and begin the feedback loop.

PHASE 2 Academic + HR + Accounting • Month 5 – 10

Goal: Complete academic and financial ecosystem. Full Standard Plan.

## Modules Delivered

| Module | Name | Key Focus |
| --- | --- | --- |
| M4 | Academic Management | MoEST GPA logic, CAS, report cards PDF |
| M6 | Homework & Timetable | Conflict detection, submission tracking |
| M7 | HR & Payroll | PF, TDS, leave integration, salary slip PDF |
| M9 | Accounting | Double-entry GL, auto-posting from M3 and M7 |

## Module Details

M4 — Academic Management

- Exam creation with theory + practical marks

- Nepal MoEST grading — hardcoded server-side (A+ to NG)

- Continuous Assessment System (CAS) with configurable weights

- Report card PDF generation — standard, CAS, and SEE formats

- NG-risk and Liberal Promotion Policy remedial alerts

M6 — Homework & Timetable

- Homework assignment per subject/class with due date and file upload

- Student submission tracking — submitted / late / not submitted

- Timetable builder with teacher conflict detection

- Substitution management without modifying master timetable

M7 — HR & Payroll

- Staff profiles with Nepal Teacher Registry ID

- Leave management: 6 types with annual balances per Nepal labor law

- Monthly payroll: basic + allowances, PF 10%+10%, TDS calculation

- Salary slip PDF per employee, annual salary statement

- On approval: auto-posts Dr. Salary Expense → Cr. Salary Payable

M9 — Accounting & Financial Management

Competitive Advantage: Most Nepal school software has basic fee collection OR basic accounting — never both fully integrated. SchoolOS does both.

- Pre-configured chart of accounts for Nepal school operations

- Double-entry bookkeeping — every transaction records debit and credit

- Auto-posting: fee payments → journal entries (no manual input)

- Auto-posting: payroll approval → salary expense and liability entries

- Nepal IRD VAT (13%), TDS, PF compliance with export formats

- Bank reconciliation workspace with CSV import

- Budget vs actual with 85% and 100% over-budget alerts

- Financial reports: I&E, Balance Sheet, Trial Balance, Cash Flow

Integration Milestone: At Phase 2 completion: Fee collection → auto-posts to accounting. Payroll approval → auto-posts to accounting. No manual double-entry required.

PHASE 3 Auxiliary Modules • Month 9 – 14

Goal: Complete the full operational ecosystem. Reduce school reliance on any external tool.

## Modules Delivered

| Module | Name | Key Focus |
| --- | --- | --- |
| M8A | Library Management | Catalog, QR per copy, fine → fee integration |
| M8B | Transport Management | Routes, driver app, boarding push notifications |

M8A — Library

- Book catalog with title, author, ISBN, category, class suitability

- Individual barcode/QR per copy — issue, return, status tracking

- Overdue fines auto-calculated and posted to student fee account

- Lost book replacement cost charged to student fee account

- Book purchase auto-posts: Dr. Library Assets → Cr. Cash/Bank

M8B — Transport (Phase 3)

- Route and stop setup with pick-up times and vehicle assignment

- Driver profile with license expiry alerts

- Driver app: marks students boarded at each stop

- Parent push notification when child boards and is dropped

- Monthly transport attendance report per student and route

PHASE 4 AI & Scale • Month 14 – 20

Goal: Differentiate SchoolOS from every competitor with an AI layer that no traditional school software can replicate.

## AI Features

- AI-generated activity feed captions (GPT-4o Vision) — teacher posts photo, caption auto-generated

- AI developmental narrative — term portfolio for Montessori students generated from observation data

- Smart notifications — personalized timing and messaging based on parent engagement patterns

- Predictive attendance risk — flag students likely to fall below 80% threshold

- Fee default prediction — identify likely defaulters 30 days before overdue

- Anomaly detection in accounting — flag unusual expense patterns for admin review

# Team Structure

Minimum viable team for Phase 1–2 execution:

| Role | Responsibilities | Headcount |
| --- | --- | --- |
| Tech Lead | Architecture, code review, delivery | 1 |
| Backend Engineers | NestJS APIs, database, integrations | 2 |
| Frontend Developer | Next.js (React) admin dashboard | 1 |
| Mobile Developer | Flutter parent & teacher apps | 1 |
| QA Engineer | Testing, regression, UAT | 1 |

# Production Readiness Checklist

Required before any live school launch:

| Category | Requirements |
| --- | --- |
| Security | JWT rotation, rate limiting, RBAC guards, audit logs, encryption at rest for sensitive fields |
| Performance | Redis caching, PostgreSQL indexing on school_id and student_id, BullMQ queue-based jobs |
| Scalability | Multi-tenant DB design with school_id scoping, modular NestJS architecture |
| Compliance | Nepal Privacy Act 2075 consent, IRD VAT compliance, iEMIS required fields, PF/TDS reporting |
| Reliability | Offline-first attendance sync, push + SMS fallback, graceful error handling |

# Timeline Summary

| Phase | Timeline | Modules | Deliverable |
| --- | --- | --- | --- |
| Phase 0 — Foundation | Month 0–1 | Core infra, Auth, DevOps | Production-ready base |
| Phase 1 — Core MVP | Month 1–4 | M1, M2, M3, M5, M10 | Live school onboarding |
| Phase 2 — Academic + HR | Month 5–10 | M4, M6, M7, M9 | Full academic & financial system |
| Phase 3 — Auxiliary | Month 9–14 | M8A, M8B | Full operational ecosystem |
| Phase 4 — AI & Scale | Month 14–20 | AI layer | AI-powered school platform |

Key Success Factor Early launch + real school feedback loop. Don't wait for a perfect build. Ship Month 4. Learn. Iterate.

SchoolOS Pvt. Ltd.  |  Nepal  |  2026–2028  |  Version 3.0